## Sheet1
|  |  | Use Cases | Fully-Dressed Use Cases | UC Diagram | Reqs | SSD | B/D Rules | Glossary | Domain Model | Logical Architecture | Interaction Diagrams | Summary Sheet
Inception Phase
| 2006-10-09 |  | x | x |  |  | x | x | x
Iteration 2 | 2006-10-17 |  | x | x |  |  | x | x | x
Elaboration Phase
Iteration 1 | 2006-10-30 |  | x | x | x | x | x |  |  | x
Iteration 2 | 2006-11-06
Iteration 3 | 2006-11-13
Iteration 4 | 2006-11-27
Construction Phase
Iteration 1 | 2006-12-04
Iteration 2 | 2006-12-11
Transition Phase
Iteration 1 | 2006-12-18
Final Report | 2006-12-25
2006-12-25
|  | Inception Phase |  | Elaboration Phase |  |  |  | Construction Phase |  | Transition Phase | Final Report | Demo
|  | Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
Use Cases |  | 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25 | 2006-12-25
Fully-Dressed Use Cases
UC Diagram
Reqs
SSD
B/D Rules
Glossary
Domain Model
Logical Architecture
Interaction Diagrams
Summary Sheet

## Prj Artifact Checklist
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-12-04
Use Cases | bar: 2006-10-09 to 2006-12-04
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-12-04
UC Diagram | bar: 2006-10-30 to 2006-12-04
Vision | bar: 2006-10-09 to 2006-12-04
Supplementary Specs Document | bar: 2006-10-09 to 2006-12-04
B/D Rules | bar: 2006-10-09 to 2006-12-04
Glossary | bar: 2006-10-09 to 2006-12-04
Logical Architecture | bar: 2006-10-30 to 2006-12-04
Domain Model | bar: 2006-10-30 to 2006-11-27
Design Class Diagrams | bar: 2006-11-27 to 2006-12-04
(System) Sequence Diagrams | bar: 2006-10-30 to 2006-12-04
Activity Diagrams | bar: 2006-11-27 to 2006-12-04
State Machine Diagrams | bar: 2006-11-27 to 2006-12-04
Skeleton Code /Source Code | bar: 2006-11-27
(Prototype) GUI Snapshots | bar: 2006-11-27 to 2006-12-04
Principles - Good UI Design | bar: 2006-12-04
Working Program's Movie | bar: 2006-12-04
Principles - GRASP | bar: 2006-12-04
Principles - Design Patterns
Summary Sheet | bar: 2006-10-17 to 2006-10-30; 2006-11-27 to 2006-12-04
Lessons Learnt | bar: 2006-10-17; 2006-11-27
README
Demonstration
Peer Grading
Notes:

## Group 1
Group 1 - Eda ÖKTEN et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Use Cases | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-12-04; 2006-12-18
UC Diagram | bar: 2006-10-17 to 2006-12-04; 2006-12-18
Vision | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Supplementary Specs Document | bar: 2006-10-09 to 2006-12-04; 2006-12-18
B/D Rules | bar: 2006-10-09 to 2006-12-04
Glossary | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Logical Architecture | bar: 2006-10-30 to 2006-12-04; 2006-12-18
Domain Model | bar: 2006-10-30 to 2006-11-27
Design Class Diagrams | bar: 2006-11-13 to 2006-12-04; 2006-12-18
(System) Sequence Diagrams | bar: 2006-10-30 to 2006-12-04
Activity Diagrams | bar: 2006-11-13 to 2006-12-04; 2006-12-18
State Machine Diagrams | bar: 2006-11-13 to 2006-12-04; 2006-12-18
Skeleton Code /Source Code | bar: 2006-11-13 to 2006-11-27; 2006-12-18
(Prototype) GUI Snapshots | bar: 2006-11-13 to 2006-12-04; 2006-12-18
Principles - Good UI Design | bar: 2006-12-04; 2006-12-18
Working Program's Movie | bar: 2006-12-04
Principles - GRASP | bar: 2006-12-04
Principles - Design Patterns | bar: 2006-12-18
Summary Sheet | bar: 2006-10-17 to 2006-10-30; 2006-11-27 to 2006-12-04
Lessons Learnt | bar: 2006-10-17; 2006-11-27
README
Demonstration
Peer Grading
Notes: | 2006-10-09: * No need to print out details of Design Class Diagram as a separate report.

## Group 2
Group 2 - Miraç Efe LÜLECİ et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-11
Use Cases | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
UC Diagram | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
Vision | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
Supplementary Specs Document | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
B/D Rules | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
Glossary | bar: 2006-10-09 to 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
Logical Architecture | bar: 2006-11-06; 2006-11-27 to 2006-12-11
Domain Model | bar: 2006-11-06; 2006-11-27 to 2006-12-11
Design Class Diagrams | bar: 2006-11-27 to 2006-12-11
(System) Sequence Diagrams | bar: 2006-11-06 to 2006-12-04
Activity Diagrams | bar: 2006-11-27 to 2006-12-11
State Machine Diagrams | bar: 2006-11-27 to 2006-12-11
Skeleton Code /Source Code | bar: 2006-11-27 to 2006-12-11
(Prototype) GUI Snapshots | bar: 2006-11-27 to 2006-12-11
Principles - Good UI Design | bar: 2006-12-04
Working Program's Movie | bar: 2006-12-04
Principles - GRASP | bar: 2006-12-04 to 2006-12-11
Principles - Design Patterns
Summary Sheet | bar: 2006-10-17 to 2006-11-06; 2006-11-27 to 2006-12-11
Lessons Learnt | bar: 2006-10-17; 2006-11-27
README
Demonstration
Peer Grading
Notes: | 2006-10-09: R - refers to previous report.

## Group 3
Group 3 - Mehmet Yüksel YAZICI et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-12-11
Use Cases | bar: 2006-10-09 to 2006-12-04
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-12-04
UC Diagram | bar: 2006-10-30 to 2006-12-04
Vision | bar: 2006-10-09 to 2006-12-04
Supplementary Specs Document | bar: 2006-10-09 to 2006-12-04
B/D Rules | bar: 2006-10-09 to 2006-12-04
Glossary | bar: 2006-10-09 to 2006-12-04
Logical Architecture | bar: 2006-10-30 to 2006-12-04
Domain Model | bar: 2006-10-30 to 2006-11-27
Design Class Diagrams | bar: 2006-11-27 to 2006-12-11
(System) Sequence Diagrams | bar: 2006-10-30 to 2006-12-11
Activity Diagrams | bar: 2006-11-27 to 2006-12-11
State Machine Diagrams | bar: 2006-11-27 to 2006-12-04
Skeleton Code /Source Code | bar: 2006-11-27
(Prototype) GUI Snapshots | bar: 2006-11-27 to 2006-12-11
Principles - Good UI Design | bar: 2006-12-04
Working Program's Movie | bar: 2006-12-04
Principles - GRASP | bar: 2006-12-04 to 2006-12-11
Principles - Design Patterns | bar: 2006-12-11
Summary Sheet | bar: 2006-10-17 to 2006-10-30; 2006-11-27 to 2006-12-11
Lessons Learnt | bar: 2006-10-17; 2006-11-27; 2006-12-11
README
Demonstration
Peer Grading
Notes:

## Group 4
Group 4 - Celal ÇIĞIR et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-10-17; 2006-11-06 to 2006-12-11
Use Cases | bar: 2006-10-09 to 2006-10-17; 2006-11-06 to 2006-12-11
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-12-11
UC Diagram | bar: 2006-10-17; 2006-11-06 to 2006-12-11
Vision | bar: 2006-10-09 to 2006-10-17; 2006-11-06 to 2006-12-11
Supplementary Specs Document | bar: 2006-10-09 to 2006-10-17; 2006-11-06 to 2006-12-11
B/D Rules | bar: 2006-10-09 to 2006-10-17; 2006-11-06 to 2006-12-11
Glossary | bar: 2006-10-09 to 2006-10-17; 2006-11-06 to 2006-12-11
Logical Architecture | bar: 2006-11-06 to 2006-12-11
Domain Model | bar: 2006-11-06 to 2006-11-27
Design Class Diagrams | bar: 2006-11-27 to 2006-12-11
(System) Sequence Diagrams | bar: 2006-11-06 to 2006-12-11
Activity Diagrams | bar: 2006-11-27 to 2006-12-11
State Machine Diagrams | bar: 2006-11-27 to 2006-12-11
Skeleton Code /Source Code | bar: 2006-11-27
(Prototype) GUI Snapshots | bar: 2006-11-27 to 2006-12-11
Principles - Good UI Design | bar: 2006-12-04 to 2006-12-11
Working Program's Movie | bar: 2006-12-04 to 2006-12-11
Principles - GRASP | bar: 2006-12-04 to 2006-12-11
Principles - Design Patterns | bar: 2006-12-11
Summary Sheet | bar: 2006-10-17 to 2006-11-06; 2006-11-27 to 2006-12-04
Lessons Learnt | bar: 2006-10-17; 2006-11-06; 2006-11-27 to 2006-12-11
README
Demonstration
Peer Grading
Notes: | 2006-10-09: * Only the updated parts are presented in interm reports.
* A very complete, organized and through report (27/11)
* Very datailed summary and lessons learnt sections

## Group 5
Group 5 - Ethem CAN et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-12-18
Use Cases | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-12-04; 2006-12-18
UC Diagram | bar: 2006-10-17 to 2006-12-04; 2006-12-18
Vision | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Supplementary Specs Document | bar: 2006-10-09 to 2006-12-04; 2006-12-18
B/D Rules | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Glossary | bar: 2006-10-09 to 2006-12-04; 2006-12-18
Logical Architecture | bar: 2006-10-30 to 2006-12-04
Domain Model | bar: 2006-10-30 to 2006-11-27
Design Class Diagrams | bar: 2006-11-06; 2006-11-27 to 2006-12-18
(System) Sequence Diagrams | bar: 2006-10-30 to 2006-12-18
Activity Diagrams | bar: 2006-11-27 to 2006-12-04; 2006-12-18
State Machine Diagrams | bar: 2006-11-27 to 2006-12-04; 2006-12-18
Skeleton Code /Source Code | bar: 2006-11-27
(Prototype) GUI Snapshots | bar: 2006-11-13 to 2006-12-18
Principles - Good UI Design | bar: 2006-12-04
Working Program's Movie | bar: 2006-12-04
Principles - GRASP | bar: 2006-12-04; 2006-12-18
Principles - Design Patterns | bar: 2006-12-11 to 2006-12-18
Summary Sheet | bar: 2006-10-09 to 2006-10-30; 2006-11-27 to 2006-12-04
Lessons Learnt | bar: 2006-10-17; 2006-11-27; 2006-12-11
README
Demonstration
Peer Grading
Notes: | 2006-10-09: * They have submitted a report and lessons learnt/summary sheet almost every week.

## Group 6
Group 6 - Bertan GÜNDOĞDU et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25
Hard-copy Report | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-11
Use Cases | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-04
Fully-Dressed Use Cases | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-04
UC Diagram | bar: 2006-10-09; 2006-10-30 to 2006-12-04
Vision | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-04
Supplementary Specs Document | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-04
B/D Rules | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-04
Glossary | bar: 2006-10-09 to 2006-11-06; 2006-11-27 to 2006-12-04
Logical Architecture | bar: 2006-10-30 to 2006-11-06; 2006-11-27 to 2006-12-04
Domain Model | bar: 2006-10-30 to 2006-11-06; 2006-11-27
Design Class Diagrams | bar: 2006-11-06; 2006-11-27 to 2006-12-11
(System) Sequence Diagrams | bar: 2006-10-30 to 2006-11-06; 2006-11-27 to 2006-12-04
Activity Diagrams | bar: 2006-11-27 to 2006-12-04
State Machine Diagrams | bar: 2006-11-27 to 2006-12-04
Skeleton Code /Source Code | bar: 2006-11-27
(Prototype) GUI Snapshots | bar: 2006-11-27 to 2006-12-11
Principles - Good UI Design | bar: 2006-12-04
Working Program's Movie | bar: 2006-12-04
Principles - GRASP | bar: 2006-12-04
Principles - Design Patterns | bar: 2006-12-11
Summary Sheet | bar: 2006-10-17 to 2006-11-06; 2006-11-27 to 2006-12-04
Lessons Learnt | bar: 2006-10-17; 2006-11-27; 2006-12-11
README
Demonstration
Peer Grading
Notes:

## Group 7
Group 7 - Orhan KIŞLAL et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Grade | Weight | Final Report | Weight
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 |  |  | 2006-12-25
Hard-copy Report (Quality) | [10 empty] | 5 | bar: 2006-10-30; 2006-11-27; 2006-12-11
Use Cases | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Fully-Dressed Use Cases | [10 empty] | 5 | bar: 2006-10-17 to 2006-10-30; 2006-11-27; 2006-12-11
UC Diagram | [10 empty] | 5 | bar: 2006-10-17 to 2006-10-30; 2006-11-27; 2006-12-11
Vision | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Supplementary Specs Document | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
B/D Rules | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Glossary | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Logical Architecture | [10 empty] | 5
Domain Model | [10 empty] | 5 | bar: 2006-10-30
Design Class Diagrams | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
(System) Sequence Diagrams | [10 empty] | 5 | bar: 2006-10-30; 2006-11-27; 2006-12-11
Activity Diagrams | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
State Machine Diagrams | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
Skeleton Code /Source Code | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
(Prototype) GUI Snapshots | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
Principles - Good UI Design | [10 empty] | 5 | bar: 2006-12-11
Working Program's Movie
Principles - GRASP | [10 empty] | 5 | bar: 2006-12-11
Principles - Design Patterns | [10 empty] | 5 | bar: 2006-12-11
Summary Sheet | [10 empty] | 5 | bar: 2006-10-17 to 2006-10-30; 2006-11-27; 2006-12-11
Lessons Learnt | [10 empty] | 5
105
README
Demonstration
Peer Grading
Notes:

## Sheet3
Group 7 - Orhan KIŞLAL et al.
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Grade | Weight | Final Report | Weight
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 |  |  | 2006-12-25
Hard-copy Report (Quality) | [10 empty] | 5 | bar: 2006-10-30; 2006-11-27; 2006-12-11
Use Cases | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Fully-Dressed Use Cases | [10 empty] | 5 | bar: 2006-10-17 to 2006-10-30; 2006-11-27; 2006-12-11
UC Diagram | [10 empty] | 5 | bar: 2006-10-17 to 2006-10-30; 2006-11-27; 2006-12-11
Vision | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Supplementary Specs Document | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
B/D Rules | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Glossary | [10 empty] | 5 | bar: 2006-10-17; 2006-11-27; 2006-12-11
Logical Architecture | [10 empty] | 5
Domain Model | [10 empty] | 5 | bar: 2006-10-30
Design Class Diagrams | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
(System) Sequence Diagrams | [10 empty] | 5 | bar: 2006-10-30; 2006-11-27; 2006-12-11
Activity Diagrams | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
State Machine Diagrams | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
Skeleton Code /Source Code | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
(Prototype) GUI Snapshots | [10 empty] | 5 | bar: 2006-11-27; 2006-12-11
Principles - Good UI Design | [10 empty] | 5 | bar: 2006-12-11
Working Program's Movie
Principles - GRASP | [10 empty] | 5 | bar: 2006-12-11
Principles - Design Patterns | [10 empty] | 5 | bar: 2006-12-11
Summary Sheet | [10 empty] | 5 | bar: 2006-10-17 to 2006-10-30; 2006-11-27; 2006-12-11
Lessons Learnt | [10 empty] | 5
105
README
Demonstration
Peer Grading
Notes: