## Sheet1
|  |  | Use Cases | Fully-Dressed Use Cases | UC Diagram | Reqs | SSD | B/D Rules | Glossary | Domain Model | Logical Architecture | Interaction Diagrams | Summary Sheet
Inception Phase
| 2006-10-09 |  | x | x |  |  | x | x | x
Iteration 2 | 2006-10-17 |  | x | x |  |  | x | x | x
Elaboration Phase
Iteration 1 | 2006-10-30 |  | x | x | x | x | x |  |  | x
Iteration 2 | 2006-11-06
Iteration 3 | 2006-11-13
Iteration 4 | 2006-11-27
Construction Phase
Iteration 1 | 2006-12-04
Iteration 2 | 2006-12-11
Transition Phase
Iteration 1 | 2006-12-18
Final Report | 2006-12-25
2006-12-25
|  | Inception Phase |  | Elaboration Phase |  |  |  | Construction Phase |  | Transition Phase | Final Report | Demo
|  | Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
Use Cases |  | 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25 | 2006-12-25
Fully-Dressed Use Cases
UC Diagram
Reqs
SSD
B/D Rules
Glossary
Domain Model
Logical Architecture
Interaction Diagrams
Summary Sheet

## Project Artifact Checklist
| Inception |  | Elaboration |  |  |  | Construction |  | Transition | Final Report | Demo
| Iteration 1 | Iteration 2 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 1 | Iteration 2 | Iteration 1
| 2006-10-09 | 2006-10-17 | 2006-10-30 | 2006-11-06 | 2006-11-13 | 2006-11-27 | 2006-12-04 | 2006-12-11 | 2006-12-18 | 2006-12-25 | 2006-12-25
Report
Use Cases
Fully-Dressed Use Cases
UC Diagram
Vision
Supplementary Spec Doc
B/D Rules
Glossary
Logical Architecture
Domain Model
Design Class Diagrams
System Sequence Diagrams
Sequence Diagrams
Interaction Diagrams
Activity Diagrams
State Machine Diagrams
Prototype GUIs
Principles - Good UI Design
Working Program Movie
Principles - GRASP
Design Patterns
Summary Sheet
Lessons Learnt
Peer Grading